## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Create Git repository and pick job postings dataset as primary data source | MUST HAVE | Kaggle | Sukumar Divi | 3- Completed
S1 | S1 | US-001 | Apply data preprocessing and ingestion pipeline (644 rows, 25 columns) | MUST HAVE | GeeksForGeeks | Sukumar Divi | 3- Completed
S1 | S1 | US-001 | Data transformation, normalization and feature engineering (demand score, priority class) | MUST HAVE | No dependency | Sukumar Divi | 3- Completed
S1 | S1 | US-001 | Explore Enron email dataset and assess suitability for knowledge graph | SHOULD HAVE | Kaggle , GeeksForGeeks | Anushree Vanam | 3- Completed
S1 | S1 | US-001 | Present Enron findings to mentor — confirm Job Postings as final dataset | MUST HAVE | No dependency | Anushree Vanam | 3- Completed
S1 | S1 | US-001 | Prepare and present Milestone 1 PPT covering Enron analysis and dataset decision | MUST HAVE | No dependency | Anushree Vanam | 3- Completed
S2 | S2 | US-002 | Define 5 entity types (Job, Location, Department, Category, Skill) and extract from data | MUST HAVE | Milestone 1 | Sukumar Divi | 3- Completed
S2 | S2 | US-002 | Extract 4 relationship types: LOCATED_IN, IN_DEPARTMENT, BELONGS_TO, REQUIRES | SHOULD HAVE | Milestone 1 | Sukumar Divi | 3- Completed
S2 | S2 | US-002 | Build NetworkX in-memory graph and push to Neo4j Aura using Cypher | MUST HAVE | Neo4j Aura | Sukumar Divi, Anushree Vanam | 3- Completed
S2 | S2 | US-002 | Implement LLM-based NER using Groq Llama 3 to extract 125 unique skills | MUST HAVE | Groq API | Sukumar Divi | 3- Completed
S2 | S2 | US-002 | Optimize Groq API calls from 644 to 35 unique combinations (94% reduction) | MUST HAVE | Groq API | Sukumar Divi, Anushree Vanam | 3- Completed
S2 | S2 | US-002 | Validate final knowledge graph: 1298 nodes and 5243 relationships | SHOULD HAVE | No dependency | Sukumar Divi, Anushree Vanam | 3- Completed
S3 | S3 | US-003 | Load 644 jobs from Neo4j with skills and convert to LangChain Documents | MUST HAVE | Milestone 2 | Sukumar Divi, Anushree Vanam | 3- Completed
S3 | S3 | US-003 | Build FAISS local vector store with MMR retriever (fetch 30 → top 10) | MUST HAVE | FAISS | Sukumar Divi | 3- Completed
S3 | S3 | US-003 | Build RAG chain using LangChain + Groq Llama 3 (FAISS approach) | MUST HAVE | Groq API | Sukumar Divi | 3- Completed
S3 | S3 | US-003 | Build Pinecone cloud vector store RAG pipeline (Serverless, AWS us-east-1, 384-dim) | SHOULD HAVE | Pinecone API | Anushree Vanam | 3- Completed
S3 | S3 | US-003 | Align both notebooks with identical Job dataclass, Cypher query and prompt template | MUST HAVE | No dependency | Anushree Vanam | 3- Completed
S3 | S3 | US-003 | Run 8-query head-to-head FAISS vs Pinecone evaluation — produce results notebook | MUST HAVE | Both pipelines | Anushree Vanam | 3- Completed
S3 | S3 | US-003 | Prepare Milestone 3 PPT and co-present RAG findings with team | SHOULD HAVE | No dependency | Anushree Vanam | 3- Completed
S4 | S4 | US-004 | Build 6-tab Streamlit dashboard with dark glassmorphism CSS theme | MUST HAVE | Milestone 3 | Sukumar Divi | 3- Completed
S4 | S4 | US-004 | Build PyVis animated knowledge graph tab (1298 nodes, 4 physics engines) | MUST HAVE | Neo4j | Sukumar Divi | 3- Completed
S4 | S4 | US-004 | Build analytics, job explorer, world map and insights tabs with Plotly | MUST HAVE | LangChain+FAISS | Sukumar Divi | 3- Completed
S4 | S4 | US-004 | Build PyVis graph tab and RAG semantic search tab — joint integration | SHOULD HAVE | LangChain+FAISS | Sukumar Divi, Anushree Vanam | 3- Completed
S4 | S4 | US-004 | Implement Node AI Agent — click any graph node → Groq LLM instant explanation | MUST HAVE | Groq API | Sukumar Divi | 3- Completed
S4 | S4 | US-004 | Design and build SendGrid email reporting feature — Scenario 1 (node click report) | MUST HAVE | SendGrid API | Anushree Vanam | 3- Completed
S4 | S4 | US-004 | Design and build SendGrid email reporting feature — Scenario 2 (search result report) | MUST HAVE | SendGrid API | Anushree Vanam | 3- Completed
S4 | S4 | US-004 | Build generate_subgraph_image(), build_node_subgraph_data(), build_search_subgraph_data() | MUST HAVE | NetworkX / Matplotlib | Anushree Vanam | 3- Completed
S4 | S4 | US-004 | Sanitize all 6 notebooks (_PUBLIC versions) and configure .gitignore for security | MUST HAVE | Git / GitHub | Anushree Vanam | 3- Completed
S4 | S4 | US-004 | Deploy dashboard to Streamlit Cloud — configure secrets and verify live public URL | MUST HAVE | Streamlit Cloud | Sukumar Divi, Anushree Vanam | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 113.5 | 10 | 14 | 14 | 15 | 16 | 17 | 14 | 8 | 4.5 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
SPRINT 1 BACKLOG — Data Ingestion & Dataset Exploration (Weeks 1–2)
US-001 | T-101 | Create Git repository and select job postings dataset as primary data source | Wk1 D1 | Wk1 D1 | Sukumar Divi | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-102 | Apply preprocessing and data ingestion pipeline (handle missing values, duplicates) | Wk1 D2 | Wk1 D3 | Sukumar Divi | Coding | 3- Completed | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-103 | Data transformation, normalization, feature engineering (demand score, priority class) | Wk1 D4 | Wk2 D1 | Sukumar Divi | Coding | 3- Completed | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-104 | Explore Enron email dataset — assess entity richness and KG suitability | Wk1 D1 | Wk1 D3 | Anushree Vanam | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-105 | Present Enron findings to mentor — confirm Job Postings as final dataset | Wk1 D4 | Wk1 D5 | Anushree Vanam | Others | 3- Completed | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-106 | Prepare and present Milestone 1 PPT (Enron analysis + dataset decision rationale) | Wk2 D2 | Wk2 D5 | Anushree Vanam | Others | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-001 | T-107 | Milestone 1 documentation and solution showcase | Wk2 D2 | Wk2 D5 | Sukumar Divi | Others | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG — Knowledge Graph Construction (Weeks 3–4)
US-002 | T-201 | Define 5 entity types and extract entities from job postings data | Wk3 D1 | Wk3 D2 | Sukumar Divi | Coding | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-202 | Extract 4 relationship types: LOCATED_IN, IN_DEPT, BELONGS_TO, REQUIRES | Wk3 D2 | Wk3 D3 | Sukumar Divi | Coding | 3- Completed | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-203 | Build NetworkX in-memory graph with nodes and edges | Wk3 D3 | Wk3 D4 | Sukumar Divi, Anushree Vanam | Coding | 3- Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-204 | Connect Neo4j Aura and push full graph using Cypher queries | Wk3 D4 | Wk3 D5 | Sukumar Divi, Anushree Vanam | Coding | 3- Completed | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-205 | Implement Groq Llama 3 LLM-based NER to extract 125 unique skills | Wk4 D1 | Wk4 D2 | Sukumar Divi | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-206 | Optimize API calls from 644 to 35 unique job-category combinations (94% reduction) | Wk4 D2 | Wk4 D3 | Sukumar Divi, Anushree Vanam | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-207 | Validate final graph — 1298 nodes, 5243 relationships, 125 skills confirmed | Wk4 D3 | Wk4 D4 | Sukumar Divi, Anushree Vanam | Others | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG — Pinecone RAG Pipeline & FAISS vs Pinecone Evaluation (Weeks 5–6)
US-003 | T-301 | Install LangChain, FAISS, Groq, SentenceTransformers | Wk5 D1 | Wk5 D1 | Sukumar Divi | Build | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-302 | Load 644 jobs from Neo4j with skills via REQUIRES relationships | Wk5 D1 | Wk5 D2 | Sukumar Divi, Anushree Vanam | Coding | 3- Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-303 | Convert jobs to LangChain Documents with rich metadata | Wk5 D2 | Wk5 D2 | Sukumar Divi, Anushree Vanam | Coding | 3- Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-304 | Build FAISS local vector store with MMR retriever (fetch 30 → top 10) | Wk5 D3 | Wk5 D3 | Sukumar Divi | Coding | 3- Completed | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-305 | Build RAG chain: LangChain + Groq Llama 3 (FAISS approach) | Wk5 D3 | Wk5 D4 | Sukumar Divi, Anushree Vanam | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-306 | Set up Pinecone Serverless index (AWS us-east-1, 384-dim, cosine metric) | Wk5 D1 | Wk5 D1 | Anushree Vanam | Build | 3- Completed | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-307 | Build Pinecone cloud RAG pipeline — LangChain + PineconeVectorStore + Groq | Wk5 D2 | Wk5 D4 | Anushree Vanam | Coding | 3- Completed | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-308 | Align Pinecone notebook with FAISS — identical Job dataclass, Cypher, prompt | Wk5 D4 | Wk5 D5 | Anushree Vanam | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-309 | Fix skills missing from embeddings — update dataclass and Cypher OPTIONAL MATCH | Wk6 D2 | Wk6 D2 | Sukumar Divi | Others | 3- Completed | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-310 | Run 8-query head-to-head FAISS vs Pinecone evaluation — log latency per query | Wk5 D5 | Wk6 D1 | Anushree Vanam | Others | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-311 | Produce evaluation results notebook — latency table, winner analysis, conclusion | Wk6 D2 | Wk6 D3 | Anushree Vanam | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-312 | Test 12 natural language queries and validate RAG answers | Wk5 D5 | Wk6 D1 | Sukumar Divi, Anushree Vanam | Others | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-313 | Prepare Milestone 3 PPT and co-present RAG findings to mentor | Wk6 D4 | Wk6 D5 | Anushree Vanam | Others | 3- Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG — Dashboard, Email Reporting, Security & Deployment (Weeks 7–8)
US-004 | T-401 | Install Streamlit, PyVis, Plotly, pyngrok, NetworkX, Matplotlib, SendGrid | Wk7 D1 | Wk7 D1 | Sukumar Divi | Build | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-402 | Build dark glassmorphism CSS theme and sidebar layout (styles.css) | Wk7 D1 | Wk7 D2 | Sukumar Divi | Coding | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-403 | Build PyVis animated knowledge graph tab (1298 nodes, physics engine selector) | Wk7 D2 | Wk7 D3 | Sukumar Divi, Anushree Vanam | Coding | 3- Completed | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-404 | Build analytics tab — node/relationship distribution and top 20 skills charts | Wk7 D3 | Wk7 D4 | Sukumar Divi | Coding | 3- Completed | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-405 | Integrate RAG semantic search tab — FAISS/Pinecone toggle, suggestion buttons | Wk7 D4 | Wk7 D5 | Sukumar Divi, Anushree Vanam | Coding | 3- Completed | 3 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-406 | Build FAISS vs Pinecone comparison tab — latency gauges, bar chart, results table | Wk7 D5 | Wk8 D1 | Sukumar Divi | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-407 | Build world map, treemap, sunburst and priority heatmap (Insights tab) | Wk8 D1 | Wk8 D2 | Sukumar Divi | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-408 | Implement Node AI Agent — JS click-to-parent bridge, postMessage, Groq LLM explain | Wk8 D1 | Wk8 D2 | Sukumar Divi | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-409 | Build send_email_report() — SendGrid API with PNG attachment support | Wk7 D3 | Wk7 D4 | Anushree Vanam | Coding | 3- Completed | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-410 | Build generate_subgraph_image() — NetworkX + Matplotlib dark-theme PNG export | Wk7 D4 | Wk7 D5 | Anushree Vanam | Coding | 3- Completed | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-411 | Build build_node_subgraph_data() — 1-hop Neo4j fetch for clicked node | Wk7 D5 | Wk8 D1 | Anushree Vanam | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-412 | Build build_search_subgraph_data() — subgraph fetch for RAG result job IDs | Wk8 D1 | Wk8 D2 | Anushree Vanam | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-413 | Integrate Scenario 1 email — node click → AI explanation + subgraph PNG in app.py | Wk8 D2 | Wk8 D2 | Anushree Vanam | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-414 | Integrate Scenario 2 email — search results → RAG answer + job table + PNG | Wk8 D2 | Wk8 D3 | Anushree Vanam | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-415 | Add render_email_share_ui() reusable expander helper in app.py | Wk8 D3 | Wk8 D3 | Anushree Vanam | Coding | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-416 | Sanitize all 6 notebooks — generate _PUBLIC versions, replace 23 credentials | Wk8 D3 | Wk8 D4 | Anushree Vanam | Others | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-004 | T-417 | Configure .gitignore — block *_REAL.ipynb and .streamlit/secrets.toml | Wk8 D4 | Wk8 D4 | Anushree Vanam | Build | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
US-004 | T-418 | Deploy to Streamlit Cloud — configure secrets panel, verify live public URL | Wk8 D4 | Wk8 D5 | Sukumar Divi, Anushree Vanam | Build | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 1 | No impediments | Started Enron email dataset exploration — downloaded and inspected columns, entity coverage
S1 | Day 2 | Limited entity types in Enron (mainly Person, Org, Date) — fewer nodes than expected | Prepared structured comparison table: Enron vs Job Postings for KG suitability
S1 | Day 3 | No impediments | Presented Enron findings to mentor — mentor confirmed Job Postings is better suited for KG
S1 | Day 4 | No impediments | Documented mentor decision — updated team, began Milestone 1 PPT preparation
S1 | Day 5 | No impediments | Completed and presented Milestone 1 PPT covering dataset analysis and selection rationale
S2 | Day 1 | No impediments | Reviewed entity and relationship extraction approach with Sukumar; understood schema design
S2 | Day 2 | Neo4j connection issues — URI format and credential errors on first Cypher push | Collaborated with Sukumar to debug — fixed URI format and credential configuration
S2 | Day 3 | Groq model llama3-8b-8192 decommissioned — API returning model not found error | Switched to llama-3.3-70b-versatile — updated across both notebooks
S2 | Day 4 | Groq rate limit hit on 644 full rows (100K token cap reached) | Contributed to optimization strategy — reduced API calls to 35 unique job-category combinations
S2 | Day 5 | No impediments | Validated final graph: 1298 nodes and 5243 relationships confirmed in Neo4j Browser
S3 | Day 1 | Pinecone SDK version conflict with LangChain — PineconeVectorStore import error | Switched to langchain-pinecone package — resolved import and configured Serverless index
S3 | Day 2 | LangChain import errors — schema module deprecated in newer versions | Updated all imports to langchain_core — aligned both FAISS and Pinecone notebooks
S3 | Day 3 | Skills missing from embedded text — OPTIONAL MATCH not yet added to Cypher | Added OPTIONAL MATCH for skills in Cypher; aligned dataclass with Sukumar's FAISS notebook
S3 | Day 4 | Pinecone cold-start latency spike (~2868ms on first query after index re-creation) | Identified as expected AWS us-east-1 network overhead — documented in evaluation results
S3 | Day 5 | No impediments | Completed 8-query evaluation — FAISS wins 8/8 at 18.7x speed. Results notebook done. PPT prepared.
S4 | Day 1 | No impediments | Designed email reporting architecture — defined Scenario 1 (node click) and Scenario 2 (search)
S4 | Day 2 | SendGrid sender email rejected — sender not verified in account | Completed Single Sender Verification in SendGrid dashboard — email delivery confirmed
S4 | Day 3 | generate_subgraph_image() — matplotlib Tkinter backend error in headless environment | Switched to matplotlib.use('Agg') before pyplot import — PNG generation resolved
S4 | Day 4 | Real API keys found in 6 notebook cells — security risk before GitHub push | Wrote Python sanitization script — replaced all 23 credential instances with placeholders
S4 | Day 5 | No impediments | Deployed to Streamlit Cloud — live URL verified, all secrets configured in cloud secrets panel

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | Wk1 D1 | Wk2 D5 | Sukumar Divi | Build a structured evaluation framework before exploring datasets — compare entity count, relationship richness and KG expandability | Exploring datasets informally without a scoring framework before presenting to mentor | Seeking mentor feedback early and presenting findings with clear supporting data | Completed Enron vs Job Postings comparison; mentor approved Job Postings — Milestone 1 PPT delivered on time
2 | S2 | Wk3 D1 | Wk4 D5 | Sukumar Divi, Anushree Vanam | Verify Neo4j node creation counts after every Cypher batch insert before moving to relationships | Assuming Cypher inserts succeeded without checking node and relationship counts in Neo4j Browser | Collaborating on joint coding tasks — pair review catches bugs faster than solo debug | 1298 nodes and 5243 relationships confirmed; assisted API optimization from 644 to 35 calls — 94% token savings
3 | S3 | Wk5 D1 | Wk6 D5 | Sukumar Divi, Anushree Vanam | Test cloud pipeline (Pinecone) with a single query before running full evaluation to catch config issues early | Running full evaluation before verifying Pinecone index dimension and metric settings are correct | Using LangChain abstractions for portable, notebook-agnostic pipeline code that works across FAISS and Pinecone | Built complete Pinecone RAG pipeline; produced FAISS vs Pinecone evaluation — FAISS wins 8/8 queries at 18.7x speed
4 | S4 | Wk7 D1 | Wk8 D5 | Sukumar Divi, Anushree Vanam | Run a credential scan script on notebooks before any git add — make sanitization a mandatory step in workflow | Hardcoding real API keys in notebook cells even temporarily — any accidental push exposes credentials | Using .streamlit/secrets.toml + .gitignore to keep all credentials off GitHub — never in source code | Email reporting shipped (Scenario 1 + 2); all 6 notebooks sanitized (23 replacements); dashboard live on Streamlit Cloud