## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Creating GIT Repo and pick relevant dataset | MUST HAVE | No dependency | Sukumar Divi | 3- Completed
S1 | S1 | US-001 | Apply preprocessing and data ingestion process | MUST HAVE | GeeksForGeeks | Sukumar Divi | 3- Completed
S1 | S1 | US-001 | Data transformation,data normalization and data enrichment | MUST HAVE | No dependency | Sukumar Divi | 3- Completed
S1 | S1 | US-001 | Showcasing the solution | SHOULD HAVE | No dependency | Sukumar Divi | 3- Completed
S2 | S2 | US-002 | Extract entities and relationships from job data | MUST HAVE | Milestone-1 | Sukumar Divi | 3- Completed
S2 | S2 | US-002 | Build Knowledge Graph using NetworkX and Neo4j | MUST HAVE | Neo4j Aura | Sukumar Divi | 3- Completed
S2 | S2 | US-002 | LLM-based NER using Groq Llama 3 to extract skills | MUST HAVE | Groq API | Sukumar Divi | 3- Completed
S2 | S2 | US-002 | Validate graph with 1298 nodes and 5243 relationships | SHOULD HAVE | No dependency | Sukumar Divi | 3- Completed
S3 | S3 | US-003 | Integrate LangChain + FAISS vector store | MUST HAVE | Milestone 2 | Sukumar Divi | 3- Completed
S3 | S3 | US-003 | Build RAG pipeline with Groq Llama 3 | MUST HAVE | Groq API | Sukumar Divi | 3- Completed
S3 | S3 | US-003 | Implement MMR semantic search over 644 jobs | MUST HAVE | FAISS | Sukumar Divi | 3- Completed
S3 | S3 | US-003 | Test RAG pipeline with 12 natural language queries | SHOULD HAVE | No dependency | Sukumar Divi | 3- Completed
S4 | S4 | US-004 | Build interactive Streamlit dashboard | MUST HAVE | Milestone 3 | Sukumar Divi | 2- In Progress
S4 | S4 | US-004 | Add PyVis graph visualization with 1298 nodes | MUST HAVE | Neo4j | Sukumar Divi | 2- In Progress
S4 | S4 | US-004 | Integrate RAG semantic search in dashboard | MUST HAVE | LangChain+FAISS | Sukumar Divi | 2- In Progress
S4 | S4 | US-004 | Deploy dashboard using ngrok from Google Colab | SHOULD HAVE | ngrok | Sukumar Divi | 2- In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 64 | 9 | 11 | 10 | 9 | 6 | 10 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T-101 | Create Git repository and select job postings dataset | Week 1 Day 1 | Week 1 Day 1 | Sukumar Divi | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-102 | Apply preprocessing and data ingestion process | Week 1 Day 2 | Week 1 Day 3 | Sukumar Divi | Coding | 3- Completed | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-103 | Data transformation, normalization and enrichment | Week 1 Day 4 | Week 2 Day 1 | Sukumar Divi | Coding | 3- Completed | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-104 | Showcasing the solution and milestone documentation | Week 2 Day 2 | Week 2 Day 5 | Sukumar Divi | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-201 | Define entity types and extract entities | Week 3 Day 1 | Week 3 Day 2 | Sukumar Divi | Coding | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-202 | Extract relationships LOCATED_IN, IN_DEPT, BELONGS_TO | Week 3 Day 2 | Week 3 Day 3 | Sukumar Divi | Coding | 3- Completed | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-203 | Build NetworkX graph with nodes and edges | Week 3 Day 3 | Week 3 Day 4 | Sukumar Divi | Coding | 3- Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-204 | Connect Neo4j Aura and push graph using Cypher | Week 3 Day 4 | Week 3 Day 5 | Sukumar Divi | Coding | 3- Completed | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-205 | Implement Groq Llama 3 NER to extract 125 skills | Week 4 Day 1 | Week 4 Day 2 | Sukumar Divi | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-206 | Optimize API calls from 644 to 35 unique combinations | Week 4 Day 2 | Week 4 Day 3 | Sukumar Divi | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-207 | Validate final graph — 1298 nodes, 5243 relationships | Week 4 Day 3 | Week 4 Day 4 | Sukumar Divi | Others | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-003 | T-301 | Install LangChain, FAISS, Groq, SentenceTransformers | Week 5 Day 1 | Week 5 Day 1 | Sukumar Divi | Build | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-302 | Load 644 jobs from Neo4j with skills via REQUIRES | Week 5 Day 1 | Week 5 Day 2 | Sukumar Divi | Coding | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-303 | Convert jobs to LangChain documents with metadata | Week 5 Day 2 | Week 5 Day 2 | Sukumar Divi | Coding | 3- Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-304 | Build FAISS vector store with MMR retriever | Week 5 Day 3 | Week 5 Day 3 | Sukumar Divi | Coding | 3- Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-305 | Build RAG chain using LangChain + Groq Llama 3 | Week 5 Day 3 | Week 5 Day 4 | Sukumar Divi | Coding | 3- Completed | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-306 | Test 12 natural language queries and validate answers | Week 5 Day 5 | Week 6 Day 1 | Sukumar Divi | Others | 3- Completed | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-307 | Fix skills missing from embeddings — update dataclass | Week 6 Day 2 | Week 6 Day 2 | Sukumar Divi | Others | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-401 | Install Streamlit, PyVis, Plotly, pyngrok | Week 7 Day 1 | Week 7 Day 1 | Sukumar Divi | Build | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-402 | Build dark theme glassmorphism CSS styling | Week 7 Day 1 | Week 7 Day 2 | Sukumar Divi | Coding | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-403 | Build PyVis animated knowledge graph tab | Week 7 Day 2 | Week 7 Day 3 | Sukumar Divi | Coding | 3- Completed | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-404 | Build analytics tab with Plotly charts | Week 7 Day 3 | Week 7 Day 4 | Sukumar Divi | Coding | 2- In Progress | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-405 | Integrate RAG semantic search tab | Week 7 Day 4 | Week 7 Day 5 | Sukumar Divi | Coding | 2- In Progress | 3 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-406 | Build world map and insights tab | Week 8 Day 1 | Week 8 Day 2 | Sukumar Divi | Coding | 2- In Progress | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-407 | Deploy via ngrok and share URL with mentor | Week 8 Day 3 | Week 8 Day 4 | Sukumar Divi | Coding | 2- In Progress | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 1 | No impediments | Set up Git repo and selected job postings dataset
S1 | Day 2 | Missing columns in dataset | Applied preprocessing and normalization
S1 | Day 3 | No impediments | Completed data transformation and enrichment
S2 | Day 1 | No impediments | Defined entity types and extracted entities
S2 | Day 2 | Neo4j connection issues | Updated credentials and fixed URI format
S2 | Day 3 | Groq model llama3-8b decommissioned | Switched to llama-3.3-70b-versatile
S2 | Day 4 | Rate limit hit on Groq API (100K tokens) | Optimized to 35 unique API calls instead of 644
S2 | Day 5 | No impediments | Validated graph with 1298 nodes and 5243 relationships
S3 | Day 1 | LangChain import errors — schema module deprecated | Updated imports to langchain_core
S3 | Day 2 | Skills missing from embedded text | Added OPTIONAL MATCH for skills in Cypher query
S3 | Day 3 | Hard MATCH dropping jobs without department | Changed to OPTIONAL MATCH for department
S3 | Day 4 | No impediments | Tested 12 queries successfully
S4 | Day 1 | No impediments | Started Streamlit dashboard development
S4 | Day 2 | No impediments | Building graph visualization with PyVis

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | Week 1 Day 1 | Week 2 Day 5 | Sukumar Divi | Document each preprocessing step clearly | Skipping data validation checks | Checking data quality at each step | Completed data ingestion pipeline with proper validation
2 | S2 | Week 3 Day 1 | Week 4 Day 5 | Sukumar Divi | Optimize API calls before running on full dataset | Running LLM on all rows without checking unique combinations | Using Neo4j Cypher for all graph operations | Reduced API calls from 644 to 35 saving time and tokens
3 | S3 | Week 5 Day 1 | Week 6 Day 5 | Sukumar Divi | Validate embedded text includes all relevant fields | Using hard MATCH which drops valid rows | Using LangChain for RAG pipeline | Fixed skills in embeddings and OPTIONAL MATCH for department
4 | S4 | Week 7 Day 1 | Week 8 Day 5 | Sukumar Divi | Test dashboard on different screen sizes | Hardcoding credentials in app.py | Using Streamlit for rapid dashboard development | Deploying via ngrok for live demo to mentor