## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | Load and preprocess Enron dataset | Must Have | None | Sathya R V | Completed
Sprint 1 | Sprint 1 | US02 | Clean and normalize email data | Must Have | US01 | Sathya R V | Completed
Sprint 1 | Sprint 1 | US03 | Extract communication edges (From-To) | Must Have | US02 | Sathya R V | Completed
Sprint 2 | Sprint 2 | US04 | Apply Named Entity Recognition (NER) | Must Have | US03 | Sathya R V | Completed
Sprint 2 | Sprint 2 | US05 | Extract entities (Person, Org, Location) | Must Have | US04 | Sathya R V | Completed
Sprint 2 | Sprint 2 | US06 | Build knowledge graph using Neo4j | Must Have | US05 | Sathya R V | Completed
Sprint 3 | Sprint 3 | US07 | Load graph data from Neo4j | Must Have | US06 | Sathya R V | Completed
Sprint 3 | Sprint 3 | US08 | Convert data to LangChain documents | Must Have | US07 | Sathya R V | Completed
Sprint 3 | Sprint 3 | US09 | Generate embeddings using transformers | Must Have | US08 | Sathya R V | Completed
Sprint 3 | Sprint 3 | US10 | Store embeddings in FAISS vector DB | Must Have | US09 | Sathya R V | Completed
Sprint 3 | Sprint 3 | US11 | Implement MMR similarity search | Must Have | US10 | Sathya R V | Completed
Sprint 3 | Sprint 3 | US12 | Integrate Groq Llama 3 for answer generation | Must Have | US11 | Sathya R V | Completed
Sprint 4 | Sprint 4 | US13 | Develop dashboard UI | Must Have | US12 | Sathya R V | Completed
Sprint 4 | Sprint 4 | US14 | Implement FAISS vs Pinecone comparison | Must Have | US13 | Sathya R V | Completed
Sprint 4 | Sprint 4 | US15 | Add user query input for semantic search | Must Have | US13 | Sathya R V | Completed
Sprint 4 | Sprint 4 | US16 | Visualize knowledge graph in dashboard | Should Have | US13 | Sathya R V | Completed
Sprint 4 | Sprint 4 | US17 | Integrate Gmail notification system | Should Have | US12 | Sathya R V | Completed
Sprint 4 | Sprint 4 | US18 | Integrate Slack webhook for output sharing | Should Have | US12 | Sathya R V | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 59 | 9 | 14 | 14 | 13 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US01 | T01 | Load dataset using pandas | 01-Feb-2026 | 02-Feb-2026 | Sathya R V | Data ingestion | Done | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US02 | T02 | Clean null and missing values | 02-Feb-2026 | 03-Feb-2026 | Sathya R V | Data preprocessing | Done | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T03 | Extract sender-receiver edges | 03-Feb-2026 | 05-Feb-2026 | Sathya R V | Feature extraction | Done | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US04 | T04 | Apply NER model | 06-Feb-2026 | 08-Feb-2026 | Sukumar Divi | NLP processing | Done | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | T05 | Extract entities (Person, Org, Location) | 08-Feb-2026 | 10-Feb-2026 | Anushree Vanam | Entity extraction | Done | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US06 | T06 | Build graph in Neo4j | 10-Feb-2026 | 12-Feb-2026 | Sukumar Divi | Graph creation | Done | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US07 | T07 | Load data from Neo4j | 13-Feb-2026 | 14-Feb-2026 | Sukumar Divi | Data loading | Done | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US08 | T08 | Convert to LangChain documents | 14-Feb-2026 | 15-Feb-2026 | Anushree Vanam | Data transformation | Done | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US09 | T09 | Generate embeddings | 15-Feb-2026 | 17-Feb-2026 | Sukumar Divi | Embedding creation | Done | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US10 | T10 | Store embeddings in FAISS | 17-Feb-2026 | 18-Feb-2026 | Sukumar Divi | Vector DB | Done | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US11 | T11 | Implement MMR search | 18-Feb-2026 | 20-Feb-2026 | Anushree Vanam | Retrieval | Done | 3 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US12 | T12 | Integrate Groq Llama 3 | 20-Feb-2026 | 22-Feb-2026 | Sukumar Divi | LLM integration | Done | 3 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US13 | T13 | Develop dashboard UI | 23-Feb-2026 | 26-Feb-2026 | Sukumar Divi | Frontend | Done | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US14 | T14 | Implement FAISS vs Pinecone comparison | 26-Feb-2026 | 02-Mar-2026 | Sukumar Divi | Backend | Done | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US15 | T15 | Add user query input | 02-Mar-2026 | 10-Mar-2026 | Anushree Vanam | Feature | Done | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US16 | T16 | Graph visualization integration | 10-Mar-2026 | 18-Mar-2026 | Anushree Vanam | Visualization | Done | 3 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US17 | T17 | Implement Gmail API for sending results | 18-Mar-2026 | 23-Mar-2026 | Sathya R V | Integration | Done | 3 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US18 | T18 | Setup Slack webhook integration | 23-Mar-2026 | 28-Mar-2026 | Sathya R V | Integration | Done | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Dataset loading issue | Fixed file path and encoding
Sprint 1 | Day 3 | Missing values in dataset | Handled null values using pandas
Sprint 2 | Day 1 | NER accuracy issue | Used LLM-based extraction
Sprint 2 | Day 4 | Graph creation errors | Fixed Neo4j queries
Sprint 3 | Day 2 | Embedding generation slow | Optimized using FAISS
Sprint 3 | Day 5 | Retrieval accuracy issue | Applied MMR search
Sprint 4 | Day 5 | Dashboard integration issues | Debugged UI and backend
Sprint 4 | Day 8 | Slack/Gmail integration unclear | Researched API and implemented basic version

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 01-02-2026 | 05-02-2026 |  | Learned data preprocessing | Avoid manual cleaning | Continue structured approach | Improved preprocessing
2 | Sprint 2 | 06-02-2026 | 10-02-2026 |  | Learned NER and graph building | Avoid incorrect entity mapping | Continue graph modeling | Improved entity extraction
3 | Sprint 3 | 11-02-2026 | 18-02-2026 |  | Learned RAG and embeddings | Avoid inefficient search | Continue optimization | Improved retrieval
4 | Sprint 4 | 19-02-2026 | 25-02-2026 |  | Learned dashboard integration | Avoid UI bugs | Continue improvements | Better UI experience
5 | Sprint 4 | 26-02-2026 | 29-02-2026 | Sathya R V | Learned API integration | Avoid delay in implementation | Continue integration features | Improved system usability